## Gantt Chart
[6 empty] | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13
Task Name | Track | Progress | Assigned by | Start Date | End Date | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1
Compile Software Requirements Specification (SRS) | Phase 1: Inception | Done | Ranuga | 2026-07-05 | 2026-07-10
Compile and edit Feasibility Study document | Phase 1: Inception | Done | Vinma | 2026-07-07 | 2026-07-12
Write Software Architecture Specification (SAD) | Phase 1: Inception | Done | Ranuga | 2026-07-07 | 2026-07-12
Compile and update Gantt Chart scheduling documentation | Phase 1: Inception | Done | Ranuga | 2026-07-09 | 2026-07-13
Establish team GitHub repository and permissions | Phase 1: Inception | Done | Ranuga | 2026-07-05 | 2026-07-07
Set up Kaggle and Google AI Studio environments | Phase 1: Inception | Done | Sineth | 2026-07-07 | 2026-07-09
Set up HuggingFace and W&B experiment tracking profiles | Phase 1: Inception | Done | Vinma | 2026-07-09 | 2026-07-11
Research existing multi-agent ticketing architectures | Phase 1: Inception | Done | Ranuga | 2026-07-12 | 2026-07-15
Elicit and compile system functional requirements | Phase 1: Inception | Done | Sineth | 2026-07-16 | 2026-07-20
Draft initial system architectural design document | Phase 1: Inception | Done | Vinma | 2026-07-21 | 2026-07-25
Design multi-agent orchestration blackboard state schemas | Phase 2: Elaboration | Done | Ranuga | 2026-07-26 | 2026-07-29
Design database schemas for PostgreSQL and ChromaDB | Phase 2: Elaboration | Done | Sineth | 2026-07-29 | 2026-08-01
Download and profile Customer Support Tickets raw dataset | Phase 2: Elaboration | Done | Vinma | 2026-08-02 | 2026-08-04
Run exploratory data analysis (EDA) on tickets data | Phase 2: Elaboration | Done | Vinma | 2026-08-04 | 2026-08-07
Clean dataset and compile PII masking NER rules | Phase 2: Elaboration | Done | Ranuga | 2026-08-05 | 2026-08-08
Perform stratified train/validation/test split configuration | Phase 2: Elaboration | Done | Sineth | 2026-08-06 | 2026-08-08
Lock and back up held-out test dataset in read-only folder | Phase 2: Elaboration | Done | Vinma | 2026-08-07 | 2026-08-08
Lock target classification labels and schemas | Track A: Fine-Tuning | Done | Ranuga | 2026-07-15 | 2026-07-17
Create synthetic curated LMS dataset by seeding Kaggle data | Track A: Fine-Tuning | Done | Ranuga | 2026-07-17 | 2026-07-21
Write Gemini distillation labelling scripts | Track A: Fine-Tuning | Done | Vinma | 2026-07-22 | 2026-07-25
Run Gemini knowledge distillation on sampled ticket corpus | Track A: Fine-Tuning | Done | Sineth | 2026-07-26 | 2026-07-30
Audit token cost and api request latency metrics | Track A: Fine-Tuning | Done | Sineth | 2026-07-31 | 2026-08-02
Verify Gemini labels manually against spot-check set | Track A: Fine-Tuning | Done | Ranuga | 2026-08-03 | 2026-08-05
Format distilled data into instruction-tuning layout | Track A: Fine-Tuning | Done | Vinma | 2026-08-06 | 2026-08-08
Choose target open-weight model architectures | Track A: Fine-Tuning | Done | Sineth | 2026-08-09 | 2026-08-10
Configure LoRA/QLoRA 4-bit training scripts | Track A: Fine-Tuning | Done | Ranuga | 2026-08-11 | 2026-08-14
Fine-tune Qwen/Qwen2.5-3B-Instruct model (Complete) | Track A: Fine-Tuning | Done | Ranuga | 2026-08-15 | 2026-08-18
Fine-tune Llama-3.2-3B-Instruct model (Complete) | Track A: Fine-Tuning | Done | Vinma | 2026-08-15 | 2026-08-18
Fine-tune Gemma-3-1B model (Complete) | Track A: Fine-Tuning | Done | Sineth | 2026-08-15 | 2026-08-18
Iterate on model hyperparameters and apply early stopping | Track A: Fine-Tuning | Done | Ranuga | 2026-08-19 | 2026-08-21
Fine-tune meta-llama/Llama-3.1-8B-Instruct (In Progress) | Track A: Fine-Tuning | In Progress | Ranuga | 2026-08-22 | 2026-08-26
Fine-tune Mistral-Ministral-3B model (Complete) | Track A: Fine-Tuning | Done | Vinma | 2026-08-22 | 2026-08-26
Fine-tune Gemma-3-4B model (Complete) | Track A: Fine-Tuning | Done | Sineth | 2026-08-22 | 2026-08-26
Log and verify validation loss convergence curves | Track A: Fine-Tuning | Done | Ranuga | 2026-08-27 | 2026-08-30
Build baseline RAG implementation using Gemini API key | Track B: LangGraph | Done | Ranuga | 2026-07-15 | 2026-07-19
Build redaction_node utilizing local spaCy NER models | Track B: LangGraph | Done | Ranuga | 2026-07-20 | 2026-07-24
Build classification_node with Gemini fallback routing | Track B: LangGraph | Done | Sineth | 2026-07-25 | 2026-07-29
Build routing_node with v3 explicit flip loops | Track B: LangGraph | Done | Ranuga | 2026-07-30 | 2026-08-03
Build validation_node with policy checklist | Track B: LangGraph | Done | Vinma | 2026-08-04 | 2026-08-08
Build gated judge validation check node | Track B: LangGraph | Done | Sineth | 2026-08-09 | 2026-08-13
Build escalation_node and handoff package builder | Track B: LangGraph | Done | Vinma | 2026-08-14 | 2026-08-18
Test end-to-end orchestration using baseline Gemini run | Track B: LangGraph | Done | Ranuga | 2026-08-19 | 2026-08-23
Define Spring Boot and Next.js contract schemas | Phase 4: Integration | In Progress | Ranuga | 2026-08-31 | 2026-09-02
Implement model service healthcheck logic | Phase 4: Integration | In Progress | Sineth | 2026-08-31 | 2026-09-02
Validate response format gateway JSON mappings | Phase 4: Integration | In Progress | Vinma | 2026-08-31 | 2026-09-02
Build Spring Boot API Gateway controllers | Phase 4: Integration | Pending | Vinma | 2026-09-03 | 2026-09-07
Implement Spring Security JWT auth filters | Phase 4: Integration | Pending | Sineth | 2026-09-03 | 2026-09-07
Configure JPA Hibernate ORM with optimistic locking | Phase 4: Integration | Pending | Vinma | 2026-09-08 | 2026-09-12
Build Next.js React ticket submission form | Phase 4: Integration | Pending | Ranuga | 2026-09-08 | 2026-09-12
Build Next.js Human Review Dashboard screen | Phase 4: Integration | Pending | Ranuga | 2026-09-13 | 2026-09-16
Assemble multi-container Docker Compose config profiles | Phase 4: Integration | Pending | Sineth | 2026-09-13 | 2026-09-16
Docker Compose: wire orchestration + ml_finetuning together | Phase 4: Integration | Pending | Sineth | 2026-09-17 | 2026-09-19
Run final held-out test evaluation benchmarks | Phase 5: Evaluation | Pending | Ranuga | 2026-09-20 | 2026-09-22
DSE: Generate baseline model performance metrics | Phase 5: Evaluation | Pending | Sineth | 2026-09-20 | 2026-09-22
DSE: Compute class-weighted dataset imbalance metrics | Phase 5: Evaluation | Pending | Vinma | 2026-09-20 | 2026-09-22
DSE: Plot final model comparative evaluation charts | Phase 5: Evaluation | Pending | Vinma | 2026-09-23 | 2026-09-25
Conduct ablation studies comparing Single-LLM vs. Agents | Phase 5: Evaluation | Pending | Ranuga | 2026-09-23 | 2026-09-25
Write up data limitations and final evaluation sections | Phase 5: Evaluation | Pending | Vinma | 2026-09-23 | 2026-09-25
Verify containerized pipeline and run staging tests | Phase 5: Evaluation | Pending | Sineth | 2026-09-26 | 2026-09-28
Perform final system bug-fixing and visual polish | Phase 5: Evaluation | Pending | Vinma | 2026-09-29 | 2026-10-01
Support symposium demo day and project presentation | Phase 5: Evaluation | Pending | Ranuga | 2026-09-30 | 2026-10-01